Short summary of collaboration discussion, 14-Sep-02

Peter Kammel

# Subsystem status and issues

| subsystem status |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | MoU item | 2002 |  | 2003 |  |
| Detectors |  |  |  |  |  |  |  |
| mPC1 |  | PNPI | PNPI1 | ok |  |  |  |
| mPC2 |  | PSI/PNPI | PNPI1, PSI1 | ok |  |  |  |
| TPC |  | PSI/PNPI | PSI1, PNPI1 | assembly |  |  |
| ePC1 |  | PSI/UIUC | PSI3, UIUC1 | ok |  |  |  |
| ePC2 |  | PSI/UIUC | PSI3 |  |  | construction |  |
| ESC |  | UIUC | UIUC3 | production |  |  |  |
| Electronics |  |  |  |  |  |  |  |
| anode |  | UIUC/PNPI | UIUC2 | production |  |  |  |
| cathode |  | UIUC/PNPI | UIUC2 | production |  |  |
| TPC |  | PNPI/PSI/UCB | PNPI1,PSI4,UCB3 | ok |  |  |  |
| DAQ |  | UCB | UCB1,2 | all purchased |  |  |
| ePC TDC |  | UCL | UCL1 | production |  |  |
| support structure |  |  |  |  |  |  |
| hydrogen vessel | PSI | PSI2 | ok |  |  |  |
| ePC, eSC support | UIUC | UIUC4 | production |  |  |  |
| gas system |  |  |  |  |  |  |
| H2 vessel, window | PSI | PSI1 | ready |  | window improvements |  |
| pump system | PSI | PSI1 | ok |  |  |  |
| Protium production | PSI/PNPI | PNPI1,PSI5 | Polluted, new ok |  | construction |  |
| Chromatography | PNPI | PNPI2 | ok |  |  |  |
| cleaning system | PNPI | PNPI1 | old polluted, new under design |  | construction |  |
| circulation system | PNPI | PNPI1 |  |  | construction |  |
| Isotope separation | PNPI | PNPI1 | ISTC proposal ? |  |  |
| Isotope monitoring |  |  |  |  |  |
| Magnet |  | UCB | UCB4 | ok |  |  |  |

We discussed the subsystem status, problems and agreed on several good solutions.

- MPC2, TPC
Commissioning of TPC has priority and participation of PNPI colleagues in this work would be very helpful, because of joint learning and information exchange. PNPI mPC2 should be brought to PSI as backup, to be used depending on run situation.

- EPC, eSC
Peter reported progress on construction of electron detectors and support structure. Although the schedule is tight, there is a good chance to have full eDet ready for the last weeks of the run.

- Hydrogen vessel window
Claude reported about single window failure and long term test of double foil window. The double foil  survived so far 2 months at 16 bar with over 30 cycles. Still concern was raised about safety, including the questions:
Does world experience with double windows exist? (info from LBL or Gatchina engineers?)
Hydrogen effects (embrittlement) should be tested.
More cycles should be made.
Pumping the outer side might not solve the problem.
For the short term Claude will expose the test setup to hydrogen and then test again.
PNPI agreed to perform independent tests and got a foil and spare flange parts from Claude (thanks Alexei).
For next year, Gatchina will try to develop a Be window to be mounted on a new entrance flange.

- Hydrogen vessel
PNPI raised concerns that leaks in the ceramaseal feedthrough will pollute the TPC. These worrys, however, appeared contradictory to Claude’s direct measurement that the chamber maintains a <10-4  mbar vacuum over a period of a week. The leak detector indicates leakages of the order 10-8  mbar-l/s. The ultimate test must be impurity analysis of gas samples taken during the run in regular time intervals.

- Gas system
A lot of discussion focused on this complex and important issue. We discussed the procedure for this year and the plan for next year separately.
This year: Claude has received new protium water and started production with the Canadian protium generator. Also, he purchased and received a new Pd filter and ordered a hydride storage/compressor unit. However, the compressor will only arrive middle of October and probably the TPC should be filled earlier. Fortunately a solution to the compressor problem was found, since an unpolluted zeolite compressor can be recovered from the present gas system. Accordingly the chemists should come earlier in October to help protium production.
Next year: Currently the recirculation system is being developed in Gatchina with CRDF funding. The options whether to assemble it in Gatchina or PSI was discussed. Eventually a good solution was found that a complete working system will be assembled in Gatchina. The collaboration (Kentucky, if necessary with the help of other institutions) will purchase a second hydrogen generator for PNPI and PNPI will upgrade the chromatography in Gatchina. 
Related to this the question, it was discussed where the protium will be produced and how it will be transported. We have conflicting statements conc. the effort of protium production. Gatchina says this is weeks of work, while Claude says these are a few days. We have to clarify this point because it impacts where our main protium amount will be produced.

- We had several discussions about isotopic separation and monitoring. Alexei and Peter agree that we should make a concerted effort to try to get ISTC funding, Alexei even hoped to get started with Arzamas before that. 
Based on this year’s disastrous experience, isotopic monitoring has high priority. There are different levels. A 10ppm sensitivity now would be helpful to prevent disastrous pollution. Claude is trying to achieve that with a mass spec, but as of this writing the prospects are still unclear. Peter initiated contacts with the AMS lab at ETH and we will visit it this Thursday. Alexei pointed out the advantage of assembling the system in Gatchina, because the analysis within Russia can be arranged. For the short term Claude will prepare a sampling volume, so that both water and gas of the new Canadian water can be analyzed in Russia as soon as possible.

# Schedule for this fall

I compiled a tentative plan below, following our discussion. I will update the list of collaboration presence on the main webpage as soon as we get the dates from Gatchina. Fortunately, in spite of financial difficulties, we can expect a strong PNPI contingent, in addition to the US and European collaborators listed already.

|  | 2-Sep | 9-Sep | 16-Sep | 23-Sep | 30-Sep | 7-Oct | 14-Oct | 21-Oct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| tasks |  |  |  |  |  |  |  |  |
| muE4 area | setup and beam time until 12/9/02 |  |  |  |  |  |
| ePC/SC |  | ePC/SC setup | ePC/SC test run |  |  |  | ePC complete setup |
| TPC |  |  |  |  |  |  | TPC into area and test |
| combined |  |  |  |  |  |  |  |  |
| mPC+TPC |  |  |  |  |  |  |  |  |
|  |  |  |  |  | TPC assembly and test |  |  |
| ePC |  |  |  |  |  |  |  |  |
|  |  | ePC/SC setup |  |  | finish ePC electronics, all channels | complete setup |
|  |  |  |  |  |  | try to get kammer 4 operational |  |
|  | DAQ shipping |  |  |  |  | assemble & test gondola's |  |
|  | 2-3 gondola ship |  |  |  |  |  |  |
| eSC |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | build det @UIUC |
| gas system |  |  |  |  |  |  |  |  |
| DAQ |  |  |  |  |  |  |  |  |
|  | run ePC/SC DAQ | VME/PVIC DMA |  |  |  |  | integrate full DAQ |
|  |  | Include TDC400 | online compression |  |  | readout TPC full speed, compression |
|  |  | include WFD's |  |  |  |  |  |  |
|  |  |  |  | prepare FADC |  |  |  |  |

|  | 28-Oct | 4-Nov | 11-Nov | 18-Nov | 25-Nov | 2-Dec | 9-Dec |
| --- | --- | --- | --- | --- | --- | --- | --- |
| tasks |  |  |  |  |  |  |  |
| muE4 area | setup and run until 12/9/02 |  |  |  |  |
|  | eDet complete DAQ |  |  |  |  |  |  |
|  |  | final TPC beam tests |  | install full eSC |  |  |  |
|  |  | Integration | data taking |  |  |  |  |
| mPC+TPC |  |  |  |  |  |  |  |
| ePC |  |  |  |  |  |  |  |
| eSC |  |  |  |  |  |  |  |
|  | assemble eSC offline |  |  |  |  |
|  | Ship gondola and support structure |  |  |  |  |  |  |
| gas system |  |  |  |  |  |  |  |
| DAQ |  |  |  |  |  |  |  |