## UIUC
mCap | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct
| 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21
runs
[9 empty] | 5/1-6/15 | [13 empty] | 8/13-10/15
[17 empty] | mLan 7/2-7/30 | [9 empty] | mLan 9/25-10/29
UIUC @ PSI
Steve | [10 empty] | mCrun I | [11 empty] | mCrun II
Peter | [10 empty] | run, ePC |  | EMC |  | vac |  | mLrun I |  |  |  | some vac |  |  |  | UI
Cenap | [12 empty] | ePC |  | EMC |  | mLrun I
UIUC student | [12 empty] | ePC
tasks mCap @PSI
commision TPC
TPC + eDet integration
combined data taking
ePC commissioning
ePC integration
final commisioning
running
individual tasks
Steve | [11 empty] | 5/24 -6/29 PSI |  |  |  |  | vac |  |  | 7/21- PSI
analysis rep. iinternal
update mu prog
analysis plan
cables, purchase?
Cenap | [8 empty] | 4/27-5/13 | [5 empty] | 6/15 PSI
LED layout
LED purch constr
stop MC
efficiency monitoring study
chamber arms
install LED
mag field studies, data analysis
Peter | [10 empty] | 5/14-6/2 |  |  | 6/7-6/21 |  | 6/25 PSI
window
analysis plan
slow control devices
LB500
student | [10 empty] | 5/18 UIUC | [5 empty] | 7/1 PSI 6 weeks
| 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21 | 1 | 8 | 15 | 21
| Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct

## tasks
people and tasks
Steve | analysis
Crun I
ePC2 help, install
Peter | Crun I
ePC
EPC
Lrun I
Cenap | systematics for | mCap | mLan
LED
analysis
ePC
Crun II
EMC
Lrun II
2004 MuCap analysis
Undergrad | ePC

## improve
summary and improvements
detectors |  |  | improvements
| ePC1 | fine | equalize thresholds, current monitor, slow control gas system, x camera
| ePC2 | not yet, noise problems | manufacture cables, organize constr, contact Joachim
| mPC1 | ok..
| eSC | fine | LED
DAQ | efficiency | 25-40%, factor 3 missing
stable
electronics | data qual | ok, with problems | get FPGA running
compressor | fine | noise generation | HV from backplane, additional VME crate, pulser timing
WFD | fine | effort, integration! | integration, DAQ meeting
clock |  |  | Boston, atomic ref?
magnet | fine |  | two axis, how?, slow control, hall probe
gas |  |  | isotope separation, monitoring
work out pud idea
hydrogen fuel cell
contact Arkadi
circulation
TPC
support |  | ePC | new chamber arms (Cenap)
proximity sensors?
data storage |  |  | NCSA?, purchase
general |  |  | Joachim

## plan03
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
runs
[5 empty] | TPC comm | Integration |  |  | physics
subsystems
detectors
mPC1
mPC2
TPC | Jan: PSI TPC tests
PNPI TPC, mPC2 tests
ePC1 | Feb: e gauges, current meter
ePC2
Ring manufact., prep. | bar: Jan to Feb
Cylinder manufacture | bar: Mar
Cathode print solder | bar: Apr
Wire soldering | bar: May
Final assemble, Conditioning testing | bar: Jun
eSC | Feb: LED pulser; May: LED install
electronics
TPC
DAQ | Mar: development; May: operation
ePC anode
ePC cathode | Apr: cables; Jun: ePC2 install
ePC TDC
fast wave form digitizer
compressor | Jan: repair, noise reduction, HV from backplane, 2nd VME crate
slow control | Jan: develop MIDAS etc
support structure
hydrogen vessel
ePC, eSC support | Feb: ePC arms
gas system
H2 vessel, window | Feb: Be window
second vessel
pumping system
protium production
chromatography
gas cleaning system | Jan: develop ciculation system
additional isotope separation | Jan: contact Arzamas
magnet
solenoid field?
explanations
gen tasks | bar: Jan
UIUC tasks | bar: Jan
UIUC minor task | bar: Jan